Coastal Cash and Shelter Recovery

ECHO proposal, evidence pack, and reporting schedule for app demo upload

| Project code | ADPC-DEMO-901 |
| --- | --- |
| Funder | ECHO |
| Sector | Shelter & Cash Assistance |
| Country | Mozambique |
| Geographic focus | Cabo Delgado and Nampula coastal displacement corridors |
| Project manager | Ana Ribeiro |
| Project period | 2026-09-01 to 2027-08-31 |
| Total budget | USD 2,350,000 |
| Target beneficiaries | 38,400 people / 6,400 crisis-affected households |
| Status | Implementation-ready |

# Executive Summary

Coastal Cash and Shelter Recovery is an ECHO-funded humanitarian action supporting cyclone- and conflict-affected households in northern Mozambique. The action combines emergency shelter kits, multipurpose cash transfers, settlement safety support, market monitoring, post-distribution monitoring, and community complaints channels.

The project is designed for families displaced along coastal and peri-urban corridors, with priority for female-headed households, older persons, people with disabilities, and households hosting separated children.

# Objective and Outcomes

- Objective: Restore dignified, safe living conditions and stabilize household purchasing power for displacement-affected families in Cabo Delgado and Nampula.

- Outcome 1: 6,400 households receive emergency shelter support aligned with cluster standards.

- Outcome 2: 4,800 households receive one-off multipurpose cash assistance through verified mobile money accounts.

- Outcome 3: Communities use functioning feedback channels and project teams adapt delivery based on complaints, protection risks, and market monitoring.

# Core Components

| Component | Planned activity | Target |
| --- | --- | --- |
| Shelter kits | Procure and distribute tarpaulins, rope, fixings, solar lamps, sleeping mats, and household repair guidance. | 6,400 households |
| Multipurpose cash | Deliver USD 135 equivalent one-off cash transfer to verified households through mobile money. | 4,800 households |
| Market monitoring | Track staple food, transport, shelter material, and fuel prices in six market locations. | Monthly price bulletin |
| Accountability | Operate hotline, community help desks, and referral tracking for protection-sensitive complaints. | 90% complaints closed within 14 days |
| Learning | Run post-distribution monitoring and quarterly review with district authorities and cluster partners. | Quarterly review note |

# Budget Summary

| Budget line | Amount USD | Percentage |
| --- | --- | --- |
| Shelter kits and distribution | 940,000 | 40% |
| Cash transfers and fees | 705,000 | 30% |
| Personnel and field operations | 352,500 | 15% |
| Monitoring, accountability, and learning | 164,500 | 7% |
| Security, logistics, and support costs | 188,000 | 8% |
| Total | 2,350,000 | 100% |

# Risks and Mitigation

| Risk | Rating | Mitigation |
| --- | --- | --- |
| Road access disrupted by rains | High | Pre-position shelter kits in Pemba and maintain alternate river crossing plan. |
| Market price inflation reduces cash transfer value | Medium | Review market basket monthly and escalate transfer-value adjustment to ECHO if threshold exceeds 15%. |
| Mobile money registration delays | Medium | Use two mobile money providers and maintain verified exception list for manual reconciliation. |
| Protection-sensitive complaints increase after targeting | High | Publish targeting criteria, run community validation, and refer sensitive cases through protection partners. |

# Explicit Reporting Schedule

The following reporting schedule is binding for this action and should replace generic reporting placeholders in the project management system.

| Report type | Reporting period | Due date | Required template |
| --- | --- | --- | --- |
| Inception Report | 2026-09-01 to 2026-09-30 | 2026-09-30 | ECHO Flash Response Inception Note |
| Monthly Situation Report | 2026-09-01 to 2026-09-30 | 2026-10-15 | Monthly Situation Report |
| Quarterly Donor Progress Report | 2026-09-01 to 2026-11-30 | 2026-12-15 | ECHO Flash Interim Narrative Report |
| Quarterly Donor Progress Report | 2026-12-01 to 2027-02-28 | 2027-03-15 | ECHO Flash Interim Narrative Report |
| Final Project Closeout Report | 2026-09-01 to 2027-08-31 | 2027-09-30 | Final Project Closeout Report |

# Embedded Reporting Template Annex

Annex C contains the donor-required sections for the ECHO Flash Interim Narrative Report. Generated reports must include every section. If evidence is missing, the draft must keep the section and mark it as requiring human update.

| Required section | Completion rule |
| --- | --- |
| Action overview | Summarize action number, location, reporting period, partners, and operating context. |
| Implementation progress | Describe activity progress against the workplan with dated evidence. |
| Beneficiaries reached | Provide households, individuals, gender, disability inclusion, and district breakdowns. |
| Sector results | Report shelter, cash, accountability, and market-monitoring results. |
| Financial overview | Include budget, expenditure, burn rate, variances, and forecast. |
| Accountability and complaints | Summarize complaints received, resolved, pending, and referral actions. |
| Safeguarding and environmental compliance | Confirm safeguarding incidents, referral handling, environmental screening, and mitigation actions. |
| Risks and constraints | List current risks, rating changes, and mitigation measures. |
| Lessons and next steps | Describe learning, adaptations, and next-period priorities. |
| Annexes and source list | List evidence documents, monitoring tools, photos, maps, and financial attachments. |