Q1 Field Update, PDM, and Risk Log

Coastal Cash and Shelter Recovery | Reporting period 2026-09-01 to 2026-11-30

| Project code | ADPC-DEMO-901 |
| --- | --- |
| Project | Coastal Cash and Shelter Recovery |
| Funder | ECHO |
| Prepared by | Ana Ribeiro, Project Manager |
| Document type | Progress report / Monitoring summary |
| Reporting period | 2026-09-01 to 2026-11-30 |

# Headline Results

| Indicator | Target | Achieved | Evidence note |
| --- | --- | --- | --- |
| Households verified | 6,400 | 4,120 | Verified household registry dated 2026-11-22 |
| Shelter kits distributed | 6,400 | 3,680 | Distribution lists from Pemba, Metuge, and Erati |
| Cash transfers completed | 4,800 | 2,940 | Mobile money batch reconciliation 1-3 |
| People reached | 38,400 | 22,760 | Average household size 5.5 from registration data |
| Complaints resolved within 14 days | 90% | 83% | 45 complaints received; 37 closed; 8 pending |
| Market bulletins issued | 3 | 3 | September, October, November market bulletins complete |

# Implementation Progress

- Shelter distribution reached 3,680 households across Pemba, Metuge, Erati, and Memba. Distribution teams prioritized households with damaged roof structures and verified displacement status.

- Cash transfers reached 2,940 households through two mobile money providers. Reconciliation found 96 failed transactions, of which 71 were corrected and re-sent by 2026-11-25.

- Community help desks operated at 18 distribution points. The hotline received 45 complaints: 21 targeting questions, 11 delayed SIM registrations, 8 protection referrals, and 5 requests for replacement shelter items.

- Post-distribution monitoring sampled 420 households. Eighty-seven percent reported shelter items were useful within seven days of receipt; seventy-four percent reported cash was spent primarily on food, transport, and shelter repair.

# Geographic Coverage

| District | Households verified | Shelter kits delivered | Cash transfers completed | Key constraint |
| --- | --- | --- | --- | --- |
| Pemba | 1,240 | 1,050 | 910 | High caseload at registration points |
| Metuge | 1,060 | 980 | 780 | Road delays after heavy rains |
| Erati | 940 | 820 | 690 | Mobile network outages |
| Memba | 880 | 830 | 560 | Fuel shortages affecting transport |

# Financial Snapshot

| Category | Budget USD | Spent USD | Burn rate |
| --- | --- | --- | --- |
| Shelter kits and distribution | 940,000 | 366,400 | 39% |
| Cash transfers and fees | 705,000 | 401,820 | 57% |
| Personnel and field operations | 352,500 | 118,300 | 34% |
| Monitoring, accountability, and learning | 164,500 | 43,900 | 27% |
| Security, logistics, and support costs | 188,000 | 62,500 | 33% |
| Total | 2,350,000 | 992,920 | 42% |

# Risks and Adaptations

| Risk / issue | Current rating | Evidence | Adaptation |
| --- | --- | --- | --- |
| Road access disrupted by rains | High | Metuge route closed for six days in November. | Shifted two distribution days and pre-positioned kits in Pemba. |
| Inflation reducing cash value | Medium | Market basket increased by 11% since baseline. | Continue monitoring; no transfer-value revision requested yet. |
| Mobile money registration delays | Medium | 96 failed transactions in batch 2. | Second provider activated for Erati and Memba. |
| Environmental screening certificate | Requires update | Screening checklist is drafted but signed certificate is not attached. | Human follow-up required before finalizing donor report section. |

# Next Period Priorities

- Complete remaining shelter-kit distributions in Erati and Memba.

- Close pending complaints and document referral outcomes with protection partners.

- Complete signed environmental screening certificate and attach it to the donor report annex.

- Run second PDM round with disability-disaggregated satisfaction analysis.