Distribution Reconciliation and Financial Tracker

Coastal Cash and Shelter Recovery | Evidence attachment

| Project code | ADPC-DEMO-901 |
| --- | --- |
| Document date | 2026-11-30 |
| Prepared by | Finance and Operations Team |
| Purpose | Supports financial overview and transfer reconciliation sections |

# Cash Transfer Reconciliation

| Batch | Districts | Households paid | Amount USD | Exceptions |
| --- | --- | --- | --- | --- |
| Batch 1 | Pemba, Metuge | 1,140 | 153,900 | 0 unresolved |
| Batch 2 | Pemba, Erati | 1,020 | 137,700 | 25 corrected re-sends |
| Batch 3 | Metuge, Memba | 780 | 105,300 | 25 failed transfers pending confirmation |
| Total | All active districts | 2,940 | 396,900 | 25 pending confirmations |

# Procurement and Stock Position

| Item | Procured | Distributed | Balance | Note |
| --- | --- | --- | --- | --- |
| Shelter kits | 4,200 | 3,680 | 520 | Balance reserved for Erati and Memba |
| Solar lamps | 4,200 | 3,680 | 520 | Included in shelter kits |
| Tarpaulins | 8,400 | 7,360 | 1,040 | Two per household |
| Sleeping mats | 12,600 | 11,040 | 1,560 | Three per household |

# Financial Notes

- Total expenditure through 2026-11-30 is USD 992,920, representing 42% of approved budget.

- Cash-transfer fees are within the agreed ceiling of 2.2% of transfer value.

- Twenty-five batch 3 mobile money confirmations remain pending and should be flagged if not resolved before report submission.

- The signed environmental screening certificate is not attached to this finance package.